## YE Work Plan
2024-25 YEAR-END WORK PLAN
| Activity | Due Date | Responsibility | Date Completed | Comments
Before June
1 | Keep daily workload and monthly reconciliations current, resolve issues timely. | Ongoing | Accounting Branch, Business Services and IT (for Property) |  | SCO/Agency Reconciliation, General Ledger (GL) Account Balances/Fund Reconciliation, Plan of Financial Adjustments (PFA), Office Revolving Fund (ORF), Bank Reconciliation, Encumbrances, Accounts Receivable (AR), Reimbursements, Property.
2 | Schedule/conduct year-end meetings to discuss and update work plan. | Ongoing starting on 4/2/2025 | Accounting Branch - GL |  | Ongoing, include all branches/units involved in year-end processes.
3 | Review all reverting documents. | 2025-04-03 | Accounting Branch (AP, AR, GL) |  | Review contracts and purchase orders with Business Services.
4 | Review and adjust other outstanding documents. | Ongoing | Accounting Branch (AP, AR, GL) |  | Accounts Receivable, Accounts Payable, ORF Advances, Purchase Orders, etc.
5 | Run Labor Distribution (LD) process for period 9. | 2025-04-07 | Accounting Branch - GL
6 | Last day to post transactions in period 9. | 2025-04-08 | Accounting Branch |  | Refer to Job Aid FI$Cal.184 (Run Labor Distribution).
7 | Prepare to close submodules, confirm all subsystem transactions have been posted and sent to GL, check for GL/KK mismatches. | 2025-04-09 | Accounting Branch |  | Refer to Job Aids FI$Cal.009 (Run the Month End Process) and FI$Cal.425 (GL-KK Mismatch Identification).
8 | Close period 9 submodules (AP, AR, BI, PO, and LD). | 2025-04-10 | Accounting Branch - GL |  | Refer to Job Aid FI$Cal.431 (MEC Automation Process).
9 | Run cost allocation for period 9. | 2025-04-11 | Accounting Branch - GL |  | Verify Clearing Account in the Budget Overview is zero for all enactment years.
10 | Run Asset Management depreciation process for period 9. | 2025-04-11 | Accounting Branch - GL
11 | Run the MEC automation process to close period 9 AM, PC, and GL modules. | 2025-04-15 | Accounting Branch - GL |  | Refer to Job Aid FI$Cal.431 (MEC Automation Process).
12 | Review reports and complete all period 9 reconciliations. | 4/16/2025 - 4/30/2025 | Accounting Branch, Business Services and IT (for Property) |  | SCO/Agency Reconciliation, GL Account Balances/Fund Reconciliation, PFA, ORF, Bank Reconciliation, Encumbrances, AR, Reimbursements, Property.
13 | Liquidate reverting year encumbrances (i.e., most ENY 2022 Budget Act items, ENY 2020 Federal Funds and most Capital Outlay appropriations, and re-appropriated items with a reversion date of 6/30/2025). | Ongoing | Accounting Branch - AP |  | Review contracts and purchase orders with Business Services.
14 | Obtain FY 2024-25 year-end deadlines and procedures from the SCO and FISCal CMO. | As soon as the information is available | Accounting Branch |  | Update the work plan to include SCO and FISCal processing cutoff dates. Establish/adjust department's internal cutoff dates accordingly.
15 | Send a memo to communicate internal year-end deadlines (e.g., the deadline to submit travel expense claims, contracts, purchase orders, etc.). | As soon as item #14 is available | Accounting Branch |  | Send the memo to other branches within the department.
16 | Create expenditure and cash projections to ensure sufficient appropriation and cash authority through the end of the fiscal year. | Ongoing | Accounting Branch
17 | Starting in period 11: no more posting to the reverting year Clearing Account. All reverting year transactions must be posted to the ultimate funds/appropriations. | Ongoing starting on 5/1/2025 | Accounting Branch
18 | Check the SCO website for Budgetary/Legal Basis Year-End Reporting information. | Ongoing until the information becomes available | Accounting Branch - GL |  | https://www.sco.ca.gov/ard_reporting.html
19 | Attend Finance year-end training and SCO open house. | 4/21/2025 - 6/4/2025 | Accounting Branch
20 | Run LD for period 10. | 2025-05-06 | Accounting Branch - GL |  | Refer to Job Aid FI$Cal.184 (Run Labor Distribution).
21 | If needed, manually reclassify AR Abatements that post in the Clearing Account in period 10 to allow sufficient time for cost allocation and PFA submission to the SCO. | 5/6/2025 - 5/8/2025 | Accounting Branch - AR |  | Refer to Finance's eLearning YE-A4 (Manually Reclassify AR Abatements and Reimbursements for Reverted Appropriations).
22 | Last day to post transactions in period 10. | 2025-05-08 | Accounting Branch
23 | Prepare to close submodules, confirm all subsystem transactions have been posted and sent to GL, check for GL/KK mismatches. | 2025-05-09 | Accounting Branch |  | Refer to Job Aids FI$Cal.009 (Run the Month End Process) and FI$Cal.425 (GL-KK Mismatch Identification).
24 | Close period 10 submodules (AP, AR, BI, PO, and LD). | 2025-05-12 | Accounting Branch - GL |  | Refer to Job Aid FI$Cal.431 (MEC Automation Process).
25 | If using the FI$Cal AR Auto Reclass, run and review the Summary Receivable Report by ChartFields to identify any AR items that should/should not be reclassified and make the necessary updates to the Reclass Code. | 5/12/2025 - 6/30/2025 | Accounting Branch - AR |  | Refer to: Job Aid FI$Cal.515 (AR Auto Reclass Process for ARs with Reverting Appropriations) Finance Year-End Session I Training
26 | Run the AR Auto Reclass Process for prior year AR Revenues and reverting AR Abatements and Reimbursements, and correct any errors. | 5/12/2025 - 6/30/2025 | Accounting Branch - AR |  | Refer to Job Aid FI$Cal.515 (AR Auto Reclass Process for ARs with Reverting Appropriations). If any reverting AR abatements in the Clearing Account are reclassified in period 11, ensure there will be sufficient time to submit PFA for reverting appropriations.
27 | Identify any additional AR items that need to be reclassified manually and complete the reclassification in FI$Cal AR module. | 5/12/2025 - 6/30/2025 | Accounting Branch - AR |  | Refer to Finance eLearning YE - A-4 (Manually Reclassify AR Abatements and Reimbursements for Reverted Appropriations) and YE - A-9 eLearning (Accrue Revenue).
28 | Run cost allocation for period 10. | 2025-05-13 | Accounting Branch - GL |  | Verify Clearing Account in the Budget Overview is zero for all enactment years.
29 | Run Asset Management depreciation process for period 10. | 2025-05-13 | Accounting Branch - GL
30 | Run the MEC automation process to close period 10 AM, PC, and GL modules. | 2025-05-15 | Accounting Branch - GL |  | Refer to Job Aid FI$Cal.431 (MEC Automation Process).
31 | Review reports and complete all period 10 reconciliations. | 5/16/2025 - 5/30/2025 | Accounting Branch, Business Services and IT (for Property) |  | SCO/Agency Reconciliation, GL Account Balances/Fund Reconciliation, PFA, ORF, Bank Reconciliation, Encumbrances, AR, Reimbursements, Property.
June
32 | Identify any changes needed for FY 2025-26 LD and/or cost allocation configurations, and submit the necessary change requests to FI$Cal. | Ongoing starting on 6/3/2025 | Accounting Branch - GL |  | Review positions and funding with Human Resources and Budget Office, review cost allocation plan and configuration with Budget Office.
33 | Run LD for period 11. | 2025-06-06 | Accounting Branch - GL |  | Refer to Job Aid FI$Cal.184 (Run Labor Distribution).
34 | Last day to post transactions in period 11. | 2025-06-06 | Accounting Branch
35 | Prepare to close submodules, confirm all subsystem transactions have been posted and sent to GL, check for GL/KK mismatches. | 2025-06-09 | Accounting Branch |  | Refer to Job Aids FI$Cal.009 (Run the Month End Process) and FI$Cal.425 (GL-KK Mismatch Identification).
36 | Close period 11 submodules (AP, AR, BI, PO, and LD). | 2025-06-10 | Accounting Branch - GL |  | Refer to Job Aid FI$Cal.431 (MEC Automation Process).
37 | Run cost allocation for period 11. | 2025-06-11 | Accounting Branch - GL |  | Verify Clearing Account in the Budget Overview is zero for all enactment years.
38 | Run Asset Management depreciation process for period 11. | 2025-06-11 | Accounting Branch - GL
39 | Run the MEC automation process to close period 11 AM, PC, and GL modules. | 2025-06-13 | Accounting Branch - GL |  | Refer to Job Aid FI$Cal.431 (MEC Automation Process).
40 | Review reports and complete all period 11 reconciliations. | 6/16/2025 - 6/30/2025 | Accounting Branch, Business Services and IT (for Property) |  | Any reconciling items must be corrected before period 12 is closed.
41 | Documents that need to be processed by 6/30/2025 must be received by the SCO before COB on 6/16/2025. | 2025-06-16 | Accounting Branch
42 | Confirm all reverting year AR items have been reclassified. | 2025-06-30 | Accounting Branch - AR
43 | Confirm all reverting year POs have been liquidated and closed. | 2025-06-30 | Accounting Branch - AP
44 | Confirm all executed POs and contracts for FY 2023 have been encumbered in FI$Cal. | 2025-06-30 | Accounting Branch - AP
After June
45 | Request last quarter capitalized asset inventory and reconciliation from Business Services and IT. | 2025-07-03 | Accounting Branch, Business Services and IT |  | Run reports/queries from FI$Cal and validate the additions/deduction for FY 2023-24 with Business Services and IT.
46 | Run LD for period 12. | 2025-07-07 | Accounting Branch - GL |  | Refer to Job Aid FI$Cal.184 (Run Labor Distribution).
47 | Last day to post transactions in period 12. | 2025-07-08 | Accounting Branch
48 | Prepare to close submodules, confirm all subsystem transactions have been posted and sent to GL, check for GL/KK mismatches. | 2025-07-09 | Accounting Branch |  | Refer to Job Aids FI$Cal.009 (Run the Month End Process) and FI$Cal.425 (GL-KK Mismatch Identification).
49 | Close period 12 submodules (AP, AR, BI, PO, and LD). | 2025-07-10 | Accounting Branch - GL |  | Refer to Job Aid FI$Cal.431 (MEC Automation Process).
50 | Run cost allocation for period 12. | 2025-07-11 | Accounting Branch - GL |  | Verify Clearing Account in the Budget Overview is zero for all enactment years.
51 | Run Asset Management depreciation process for period 12. | 2025-07-11 | Accounting Branch - GL
52 | Run the MEC automation process to close period 12 AM, PC, and GL modules. | 2025-07-15 | Accounting Branch - GL |  | Period 998 MODACCRL will open when period 12 is closed.
53 | Review reports and complete all period 12 reconciliations. | 7/16/2025 - 7/21/2025 | Accounting Branch, Business Services and IT (for Property) |  | There cannot be any discrepancies between department's and SCO balances, except for Report 3 item(s).
54 | Obtain June overtime and Temp Help data for payroll accrual (YE A-8 entry). | 2025-07-17 | Accounting Branch - GL
55 | Obtain contingent liabilities for year-end accruals or disclosure on Report 22. | 2025-07-17 | Accounting Branch - GL
56 | Confirm period 998 MODACCRL is open. | 2025-07-17 | Accounting Branch - GL
57 | Post year-end accrual/adjusting entries in period 998 MODACCRL. | 7/17/2025 - 7/21/2025 | Accounting Branch - GL |  | Refer to Finance year-end training and eLearning materials.
58 | Review period 998 BUDLEGAL reports and complete preliminary SCO/Agency Reconciliation. | 7/22/2025 - 7/24/2025 | Accounting Branch - GL |  | Refer to Finance year-end training. There cannot be any discrepancies between department's and SCO balances, except for Report 3 item(s).
59 | Review period 998 cost allocation configuration and statistic journal and update as necessary. | 2025-07-24 | Accounting Branch - GL
60 | Confirm all year-end accruals/adjusting entries have been posted and all reports have been reviewed for accuracy. | 2025-07-24 | Accounting Branch - GL
61 | Review the DFQ_KK_16_REIMB_RECON or the PDA report to determine if any additional YE A-3 entries are needed. | 2025-07-25 | Accounting Branch - GL |  | Refer to Finance Year-End Session I Training and YE - A-3 eLearning (Accrue AR Abatements and Reimbursements).
62 | Complete period 998 final PFA reconciliation and post pending PFA reclassification entries in period 998 MODACCRL. | 2025-07-26 | Accounting Branch - GL |  | Refer to Finance year-end training and eLearning materials.
63 | Complete period 998 final PFA reconciliation and post pending PFA reclassification entries in period 998 MODACCRL. | 2025-07-26 | Accounting Branch - GL |  | Refer to Finance year-end training and eLearning materials.
64 | Submit a request to the FSC to close period 998 MODACCRL. | 2025-07-28 | Accounting Branch - GL
65 | Upon notification from the FSC, post encumbrance liability reclassification entries. | 2025-07-30 | Accounting Branch - GL |  | Refer to Finance year-end training and eLearning materials.
66 | Confirm all encumbrance reclassification entries have been posted and notify the FSC to proceed with year-end close. | 2025-07-31 | Accounting Branch - GL
67 | Sales/Use Tax due to CDTFA, if applicable. | 2025-07-31 | AP Unit |  | Deadline to submit to Calif. Department of Tax and Fee Administration
68 | Submit Dishonored Check Workload Data to STO. | 2025-07-31 | AR Unit |  | Refer to SAM Section 8043
69 | Complete LD configuration rollover process and review the new fiscal year tables. | 2025-07-31 | Accounting Branch - GL |  | This task should be performed after period 12 LD is completed. Refer to Job Aid FI$Cal.255 (LD Configuration Roll-Over Process: Establishing New Year LD Configuration Tables).
70 | Upon notification from the FSC that YEC is finished, review and complete all final period 998 reconciliations. | 8/1/2025 - 8/4/2025 | Accounting Branch - GL
71 | Prepare and submit year-end financial reports to the SCO and other control agencies.* | 8/5/2025 - 9/2/2025 | Accounting Branch - GL
72 | Confirm the reversal journals for year-end accruals/adjusting entries that should be reversed have been posted in the new fiscal year. | 2025-08-04 | Accounting Branch - GL
73 | Review the SCO Agency Reconciliation Report against the Budget Act. | 2025-08-04 | Accounting Branch - GL
74 | Perform budget validation in FI$Cal. | 2025-08-05 | Accounting Branch - GL |  | Refer to Finance's SCO/Agency Reconciliation month-end training.
75 | Review PFA and Tree configuration, submit request to PFARequests@dof.ca.gov if updates are needed. | 2025-08-06 | Accounting Branch - GL
76 | If applicable, post statistic journal for the new fiscal year. | 2025-08-07 | Accounting Branch - GL
77 | Perform period 1 month-end close processes and complete reconciliations. | 8/8/2025 - 8/29/2025 | Accounting Branch - GL |  | Confirm beginning balances match to prior year's period 998 ending balances.
78 | Submit Detailed Fund Balance report (DF-303) and Past Year Expenditure - Reconciliation (DF-304) to Finance. | TBD | Budget Unit |  | Refer to the applicable Finance Budget Letter.
79 | Generally Accepted Accounting Principal (GAAP) information, excluding independently audited financial statements, due to the SCO. | 2025-09-30 | Accounting Branch - GL |  | Refer to the applicable Finance Budget Letter.
80 | Independently audited financial statements due to the SCO. If the financial statements are not available by this date, a draft statement must be submitted. | 2025-11-15 | Accounting Branch - GL |  | Refer to the applicable Finance Budget Letter.
81 | Submit the final financial statements if a draft is previously submitted (see item #80). | 2025-11-30 | Accounting Branch - GL |  | Refer to the applicable Finance Budget Letter.
82 | Evaluate Work Plan | After all financial reports have been submitted | Accounting Branch |  | Review what worked and how to improve for the next year-end process
* If, after issuing the year-end financial reports, a department determines that there are material differences between amounts accrued as of June 30 and subsequent events (e.g., receipts and expenditures) relating to prior year funds, the department must immediately contact the SCO, Bureau of State Government Reporting for instructions. The definition of material, for this purpose, means a net change in the total accrued income and the total accrued expenditures of $1,000,000 or more at the fund level. See SAM Section 7981.