## Year-end Plan 22-23_(Clean)
2022-23 YEAR-END WORK PLAN
# | Activity | Due Date | Responsibility | Date Completed | Comments
A. Before June 30:
April
1. | Keep daily workload current. Perform all month-end reconciliations for July 2022 thru February 2023 (period 1 to 8). | Ongoing | Accounting Office (A.O.) |  | SCO/Agency Reconciliation, PFA, Encumbrance, AR, Assets, Reimbursements, 1140 Cash, ORF, Bank Reconciliation.
2 | Review all reverting documents | 2023-04-03 | AP, AR, GL, PO
3 | Send year-end deadlines letters | 2023-04-03 | GL Unit |  | Send to Agency Division Chiefs, Boards & Commissions, and Business Services
4 | Establish year-end work plan for the current fiscal year | 2023-04-03 | GL Unit
5 | Schedule year-end meetings to discuss and update work plan | 2023-04-04 | GL Unit |  | Ongoing, include all units involved with year-end.
6 | Run Labor Distribution (LD) for period 9 | 2023-04-07 | Department/LD Unit
7 | Last day for posting in Period 9 | 2023-04-10 | Accounts Receivable (AR), Accounts Payable (AP), Purchase Order (PO), GL Units
8 | Run MEC query - ZZ_MEC_OUTSTANDING_TRXNS. | 2023-04-11 | Department |  | The ZZ_MEC_OUTSTANDING_TRXNS query is a MEC query that consolidated four existing outstanding queries (voucher, deposit, items & journal) identified in Job Aid 009. Making sure all transactions are clear is part of MEC tasks which departments must perform prior to closing their accounting period(s).
9 | Review and ensure all AR Items are posted. Main Menu > Accounts Receivables > Pending Items > Review items > Group Not Set to Post | 2023-04-11 | Department |  | These are accounts receivable activities. There should be no AR pending items at month-end.
10 | Review and adjust other outstanding documents: Payables (Due To) Receivables (Due From) Encumbrances ORF (Advances) | 4/11/2023 thru 6/15/2023 | A/P Unit A/R Unit PO Unit Office Revolving Fund (ORF) Unit |  | Ongoing
11 | Request FSC to Close Period 9 sub-modules | 2023-04-12 | Department/FI$Cal Service Center (FSC)
12 | Run Cost Allocation (CA) for Period 9 | 2023-04-13 | Department |  | Verify Clearing Account in Budget Overview is zero for all ENYs
13 | Run Asset Management (AM) Depreciation for Period 9 | 2023-04-13 | Department |  | This is done in the Departmental Adjustment Ledger
14 | Request FSC to Close Period 9 AM and General Ledger (GL) Modules | 2023-04-14 | Department/FSC
15 | Reverting year Encumbrances - Start liquidating (Bud Act ENY 2020, Federal Funds and most Capital Outlay ENY 2018). | 2023-04-14 | AP & PO Units |  | Work with PO Unit to review reverting year encumbrances for Bud Act ENY 2020 & Fed Fund ENY 2018 of items not expected to be received. (Any reverting year payments must be submitted to SCO Audits for approval by June 15, 5:00 p.m. to ensure processing by June 30 or earlier.) Refer to Job Aids 243 & 437
16 | Perform all reconciliations for March (period 9) | 2023-04-21 | A.O. |  | SCO/Agency Reconciliation, PFA, Encumbrance, AR, Assets, Reimbursements, 1140 Cash, ORF, Bank Reconciliation. Complete by 4/30.
17 | Obtain SCO Year-End Procedure letter and FI$Cal Announcement - Year-End Deadlines | 2023-04-27 | GL Unit |  | Add SCO/FI$Cal cut-off dates (June 15th) for all required documents that need to be processed at SCO by June 30th to work plan.
18 | June Expenditures per SCO Year-End Procedure letter | 2023-04-27 | GL Unit |  | Determine whether sufficient appropriation and cash authority will be available to cover June payroll and other expenditures. If not sufficient contact Finance and notify SCO by COB on June 15th.
19 | Distribute correspondence to the AR, AP, and GL Units - starting in Period 10 to post reverting year transactions to ultimate programs/funds | 2023-04-28 | GL Unit |  | Direct funded only - Do not post to Clearing Account (9999)
May
20 | Start checking SCO website for when the Budgetary/Legal Basis Year-End Financial Reports Procedure Manual is available for download | 2023-05-01 | GL Unit |  | https://www.sco.ca.gov/ard_reporting.html
21 | Year-end meetings | 2023-05-05 | A.O. |  | Ongoing
22 | Run LD for Period 10 | 2023-05-05 | Department/LD Unit |  | See Job Aid 184 (Job Running Labor Distribution)
23 | Last day for posting in Period 10 | 2023-05-08 | AR, AP, PO, GL Units
24 | Run Outstanding Transaction Queries | 2023-05-11 | Department |  | Job Aid 009 (Run the Month End Process)
25 | Ensure all Items are posted. Main Menu > Accounts Receivables > Pending Items > Review Items > Group Not Set to Post | 2023-05-11 | Department |  | These are accounts receivable activities.
26 | Request FSC to Close sub-modules for period 10 | 2023-05-12 | Department/FSC
27 | Run CA for Period 10 | 2023-05-15 | Department |  | Verify Clearing Account in Budget Overview is zero for all ENYs
28 | Run AM Depreciation for period 10 | 2023-05-15 | Department |  | This is done in the Departmental Adjustment Ledger
29 | Request FSC to Close AM and GL for Period 10 | 2023-05-18 | Department/FSC
30 | Check SCO website for Prior Year Accruals Summary Report | 2023-05-18 | GL Unit |  | If available print a copy can be use when preparing Report 15. See link below
https://www.sco.ca.gov/ard_reporting.html
31 | Review and Reclassify all reverting year AR Reimb/Abatements documents and reclass to AR-Other: Acct 1209900/1290000 (Bud Act ENY 2020) Record A-4 Entry - Reclassify Reverted Appropriations for Reimbursements and Abatements. | 2023-05-18 | AR Unit |  | YE-A-4 Reclassify AR Abatements & Reimbursement for Reverting Approp (Alt Acct 131900000) See link below
YE - A-4 – Manually Reclassify AR Abatements and Reimbursements for Reverted Appropriations (ca.gov)
32 | Perform all reconciliations for April (period 10) | 2023-05-22 | GL Unit |  | Reconciling items must be corrected in period 11.
June
33 | Prepare Labor Distribution Configuration Change Request for changes in new year, if applicable | 2023-06-05 | Department |  | Labor review with Personnel and Budget Office and allocation with Budget Office.
34 | Year-end meetings | 2023-06-06 | A.O. |  | Ongoing
35 | Run LD for Period 11 | 2023-06-07 | Department/LD Unit
36 | Last day to post in Period 11 | 2023-06-08 | AR, AP, PO, GL Units
37 | Run Outstanding Transaction Queries | 2023-06-09 | Department |  | Job Aid 009 (Run the Month End Process)
38 | Year-End Adjusting Entry Identify A-9 Revenue Accruals for reclassification of prior year revenue receivable to a deferred receivable | 2023-06-09 | Accounting Office |  | For YE adjusting entries, refer to Finance eLearning Year-End Training, Presentation - Session 1, See link below
YE - A-9 Accrue Revenue (ca.gov)
39 | Review and ensure all Items are posted. Main Menu > Accounts Receivables > Pending Items > Review Items > Group Not Set to Post | 2023-06-09 | Department |  | There should be no pending AR items at month-end
40 | Request FSC to Close sub-modules for Period 11 | 2023-06-09 | Department/FSC
41 | Run CA for Period 11 | 2023-06-12 | Department/GL |  | Reminder: Review reverting appropriations for allocation transactions. If applicable prepare a final PFA Transaction Request letter. Verify Clearing Account in Budget Overview is zero for all ENYs
42 | Run AM Depreciation for Period 11 | 2023-06-12 | Department |  | This is done in the Departmental Adjustment Ledger
43 | Request FSC to Close AM and GL for Period 11 | 2023-06-14 | Department/FSC
44 | Deadline for entering POs for year-end | 2023-06-14 | GL/PO
45 | Reminder last day - to submit documents to SCO in order to be process by June 30th | 2023-06-15 | GL Unit |  | Refer to line item #17
46 | Reminder last day - to notify SCO on insufficient appropriation and cash authority, if applicable | 2023-06-15 | GL Unit |  | Refer to line item # 17 and review the validity of outstanding POs
47 | Year-end meetings | 2023-06-15 | A.O.
48 | Perform all reconciliations for May (period 11) | 2023-06-15 | GL Unit |  | Correct reconciling items in period 12
49 | Request last quarter Capital Assets Report from Business Services | 2023-06-29 | GL/Business Services |  | Generated Capital Assets Report from FI$Cal and validate the additions/deduction for FY 22-23 with Business Services
50 | Request quarterly/annual Internally Generated Intangible Assets Report from IT | 2023-06-29 | GL/IS Unit
B. After June 30:
July
51 | Start reviewing Finance training eLearning and SCO Budgetary/Legal Basis Year-End Financial Reports Procedure Manual | 2023-07-03 | GL Unit |  | https://www.sco.ca.gov/ard_reporting.html
FI$Cal Resources for Accounting ¦ Department of Finance
52 | Year-end meetings | 2023-07-03 | A.O.
53 | Run LD for Period 12 | 2023-07-07 | Department/FSC
54 | Last day to post in Period 12 | 2023-07-10 | AR, AP, PO, GL Units
55 | Run Outstanding Transaction Queries | 2023-07-10 | Department
56 | Ensure all Items are posted. Main menu > Accounts Receivables > Pending Items > Review items > Group Not Set to Post | 2023-07-10 | Department
57 | Request FSC to close sub-modules for Period 12 | 2023-07-11 | Department/FSC
58 | Run CA for Period 12 | 2023-07-11 | Department |  | Verify Clearing Acct in Budget Overview is zero for all ENY
59 | Run AM Depreciation for Period 12 | 2023-07-12 | Department |  | This is done in the Departmental Adjustment Ledger
60 | Review all Pending Cash Transfer Accounts | 2023-07-12 | GL Unit |  | Query ZZ_PENDING_CASH_DEPT_USE will show all funds and review all pending cash account. Submit a request to FSC to run the cash reclass process.
61 | Review Trial Balance for abnormal balances | 2023-07-12 | GL Unit |  | Make appropriate adjustment, if applicable
62 | Request FSC to Close AM and GL for Period 12 | 2023-07-13 | Department/FSC
63 | Perform all reconciliations for June (period 12) | 2023-07-14 | GL Unit
64 | Update statistics journal for new year allocations basis. | 2023-07-14 | Department
65 | Request FSC to open Period 998 | 2023-07-17 | Department/FSC
66 | Year-Adjusting entries (period 998) A-3 Abatement Accruals and Reimbursement A-5 Accrual Interest Earnings on Investments A-7 Abatements for Surveyed Equipment A-9 Accrue Revenue | 2023-07-17 | Accounting Office |  | For YE adjusting entries, refer to Finance eLearning Year-End Training, Presentation - Session 1, Refer to link below
FI$Cal Resources for Accounting ¦ Department of Finance
67 | Record A-1 Entry:Record Undeposited Receipts | 2023-07-17 | AR Unit |  | Any undeposited receipts received before or on June 30th that are not deposited. Refer to Finance eLearning
68 | Record A-8 Entry - Accrual of Expenditures | 2023-07-17 | AP Unit |  | Any Goods or Services received before or on June 30th and have not been paid. Refer to Finance eLearning and YE Training Session 1 PPT. Refer to link below
FI$Cal Resources for Accounting ¦ Department of Finance
69 | Record A-2 Entry: Adjust Revolving Fund Cash Account | 2023-07-17 | ORF Unit
70 | Record A-6 Entry: Record Interest Due From Other Funds | 2023-07-17 | A.O. |  | To record SMIF fourth quarter interest
71 | Record A-10 Entry: Adj for Dishonored Checks, if needed | 2023-07-18 | A.O. |  | The A-10 entry is required for dishonored checks considered to be collectible during the next fiscal year.
72 | Record A-12 Entry: Establish Reserve for Deferred AR for Abatements and Reimbursements, if needed | 2023-07-18 | GL Unit |  | A-12 entries reclassify a portion of ARs for abatements and reimbursements that will not be collected during the new year
73 | Year-end meetings | 2023-07-18 | A.O.
74 | Run Outstanding Transaction Queries for Period 998 | 2023-07-18 | Department |  | Query ZZ_MEC_Outstanding_TRXNS and All ZZ_Outstanding Queries. See Job Aid 185, and Job Aid 009
75 | Review all Pending Cash Transfer Accounts | 2023-07-18 | GL Unit |  | Query ZZ_PENDING_CASH_DEPT_USE will show all funds and review all pending cash account. Submit a request to FSC to run the cash reclass process.
76 | Run CA for Period 998 | 2023-07-19 | Department
77 | Record year-end PFA - Reclass to Due To/From | 2023-07-19 | GL Unit |  | For PFA reclass refer to Finance eLearning Year-End Training, Presentation - Session 1, See link below
FI$Cal Resources for Accounting ¦ Department of Finance
78 | Order Report No. 7, Subsidiary on File | 2023-07-19 | GL |  | Validate fund affiliate are populated
79 | Due To/From Other Funds/Apropriations/Other Government/Federal Governement | 2023-07-19 | GL |  | Validate BU affiliate and fund affiliate are populated
80 | Last day to post in Period 998 | 2023-07-19 | A.O. |  | Last day for Year-End adjustments/corrections. Run a Trial Balance to ensure there are no abnormal balances
81 | Complete Final Period 998 reconciliations | 2023-07-19 | GL Unit |  | SCO/Agency Reconciliation, PFA, Encumbrance, AR, Assets, Reimbursements, 1140 Cash, ORF, Bank Reconciliation. Complete by 7/19/23.
82 | Run "Cash balance by Fund" query | 2023-07-19 | GL Unit |  | Ensure 65 and/or 1140 account(s) matches statewide BU by Fund. Run query before BLL. Shared Funds = run all Fiscal Years 65 and/or account (fund administrator). Non-Shared = only run current year 65 and/or account. Refer to FI$Cal.259 - Cash Reconciliation.
83 | Request FSC to close Period 998 and build Budgetary Legal Ledger (BLL) | 2023-07-19 | Department/FSC |  | At this point BLL will be the only ledger open.
84 | Encumbrance Reclassification - to reclassify the state suppliers to correct the Due To account | 2023-07-20 | BLL/Dept. Adj |  | Refer to Finance eLearning, Year-End Training, Presentation - Session 1, Refer to link below
FI$Cal Resources for Accounting ¦ Department of Finance
85 | Record Statewide Assessment transfers under department BU's | 2023-07-21 | BLL Only |  | Refer to Finance eLearning, Year-End Training, Presentation - Session 1, Refer to link below
FI$Cal Resources for Accounting ¦ Department of Finance
86 | Accrue 2022 General Fund Loan in Special Fund - Debit to Due From Other Funds and Credit to BLL Cash in State Treasury | 2023-07-21 | BLL Only |  | Refer to Finance eLearning, Year-End Training, Presentation - Session 1, Refer to link below
FI$Cal Resources for Accounting ¦ Department of Finance
87 | Reverse FY 2021 General Fund Loan accrual created in FY 2021 | 2023-07-21 | BLL Only |  | Refer to Finance eLearning, Year-End Training, Presentation - Session 1, Refer to link below
FI$Cal Resources for Accounting ¦ Department of Finance
88 | Reverse FY 2021 SB 84 accrual created in FY 2021 | 2023-07-21 | BLL Only |  | Refer to Finance eLearning, Year-End Training, Presentation - Session 1, Refer to link below
FI$Cal Resources for Accounting ¦ Department of Finance
91 | Year-end meetings | 2023-07-21 | A.O. |  | At this point the meeting could be more than once a week until August 31 deadline
92 | Accrue 2022 statewide assessment at Year-End - Debit to Due From and Credit to GL 65XXX Unappropriated Transfer Out | 2023-07-21 | BLL Only |  | Refer to Finance eLearning, Year-End Training, Presentation - Session 1, section on BLL. Refer to the link below
FI$Cal Resources for Accounting ¦ Department of Finance
93 | Complete a preliminary Period 998 BLL reconciliations | 2023-07-24 | GL Unit |  | Review for any adjustments for encumbrance reclass
94 | For Employee Defaults, add, change, and/or delete for new year Chart Field strings | 2023-07-25 | Department |  | This task should be done after running July labor.
95 | Complete/review final Period 998 BLL reconciliations | 2023-07-26 | GL Unit
96 | Request FSC to close Budgetary Legal Basis Ledger | 2023-07-27 | Department/FSC |  | Job Aid 258
97 | Request FSC to run YEC process | 2023-07-28 | Department/FSC
98 | Sales/Use Tax due to CDTFA, if applicable | 2023-07-31 | AP Unit |  | Deadline to submit to Calif. Department of Tax and Fee Administration
99 | Submit Dishonored Check Workload Data to STO. | 2023-07-31 | AP Unit |  | Refer to SAM Section 8043
AUGUST
100 | Run Budget Status Report (New Fiscal Year) | 2023-08-01 | GL Unit |  | Verify with Governor Budget and SCO Tab Run
101 | Conduct Labor Roll Over - to add new effective dates to the Labor System | 2023-08-02 | Department |  | Main Menu - FI$Cal Process - FI$Cal Extension - LD - LD Configuration Roll-Over
102 | Statistical Journal for allocation must be posted for all active ENY before running allocation (STATISTICS) | 2023-08-03 | Department |  | The accounting date must be 7/1. Post to Ledger Group 'Statistics'
103 | Reverse prior year and establish State Compensation Insurance Fund Advance in the new fiscal year | 2023-08-04 | GL Unit |  | GL Acct 1309200, if applicable
104 | Reverse prior year and establish Service Revolving Fund Advance in the new fiscal year | 2023-08-04 | GL Unit |  | GL Acct 1309200, if applicable
105 | Request FSC change allocation back to regular configuration | 2023-08-07 | Department |  | Due to re-configuration for period 998 allocation, if applicable
106 | Run LD for period 01 | 2023-08-09 | Department
107 | Run MEC Queries: ZZ_MEC_Entries_Not _Sent _To_GL ZZ_MEC_Outstanding_TRXNS | 2023-08-10 | Department |  | Refer to Finance Website for MEC & SCO Agency Reconciliation Training Session 1, Job Aid 037 and Job Aid 185
FI$Cal Resources for Accounting ¦ Department of Finance
108 | Correct Suspense Entries: General Ledger > Journal > Suspense Correction > Correct Suspense Entries | 2023-08-10 | Department |  | Refer to Finance Website for MEC & SCO Agency Reconciliation Training Session 1, Job Aid 033
FI$Cal Resources for Accounting ¦ Department of Finance
109 | Close sub-modules for Period 01 | 2023-08-14 | Department
110 | Begin preparing and submit all SCO Year-End Financial Reports. | 2023-08-31 | GL Unit |  | Refer to Finance Website for Year-End Training, Session 2 and Finance eLearning. Refer to link below
FI$Cal Resources for Accounting ¦ Department of Finance
111 | Prepare Report 6 - Final Budget Report | 2023-08-31 | GL Unit |  | Refer to FI$cal.235 Job Aid
112 | Prepare Report 7 - Pre-Closing Trial Balance (Modified Accrual Period 998 & BLL) | 2023-08-31 | GL Unit |  | Validate Report 7 BLL to MODACCRL (Report 7 difference s/b Encumbrances only - match with Encumbrance amounts on Final SCO Agency Recon) Refer to Job Aid FI$Cal.228 to run this report
113 | Prepare Report 8 - Post Closing Trial Balance | 2023-08-31 | GL Unit |  | Refer to Finance training and FI$Cal.229 Job Aid
114 | Prepare Report 8 - Subsidiary on File (BLL) | 2023-08-31 | GL Unit |  | Refer to Finance training and FI$Cal.256 Job Aid
115 | Prepare required manual Reports 1, 2, 3 (if applicable), 5, 15, 22, and Material Variance Form | 2023-08-31 | GL Unit |  | Governmental only - Refer to Finance YE Session II eLearning for preparing manual statements. See Year End Reports (YE-R) link below
FI$Cal Resources for Accounting ¦ Department of Finance
116 | Prepare Report 9 - Analysis of Change in Fund Balance | 2023-08-31 | GL Unit |  | Non-governmental only - Refer to Finance training and FI$Cal.254 Job Aid
117 | Prepare Report 10 - Analysis and Reconciliation of ORF Accountability | 2023-08-31 | ORF Unit |  | Internal use only. Refer to Finance training
118 | Prepare Report 11 - Reconciliation of General Cash Checking Account | 2023-08-31 | AR Unit |  | Internal use only. Refer to Finance training
119 | Prepare Report 13 - Report of Expenditures of Federal Funds | 2023-08-31 | GL Unit |  | Deadline to submit one manual or electronic copy of Report 13 to Department of Finance, Fiscal Systems & Consulting Unit (FSCU). SCO no longer requires this report.
120 | Deadline for Report 14 - Report of Bank Account Outside the Treasury System | 2023-08-31 | GL Unit |  | Deadline to submit Reports 14 to Treasurer's Office through FI$Cal
121 | Prepare Report 18 - Statement of Changes in Capital Assets | 2023-08-31 | GL Unit |  | Refer to Finance training and FI$Cal.231 Job Aid
122 | Prepare Report 19 - Statement of Capital Assets | 2023-08-31 | GL Unit |  | Refer to Finance training and FI$Cal.230 Job Aid
123 | Prepare Report 20 - Statement of Financial Condition | 2023-08-31 | GL Unit |  | Non-governmental only - Refer to Finance training and FI$Cal.232 Job Aid
124 | Prepare Certification letters | 2023-08-31 | GL Unit
125 | Review Checklist for Financial Reports | 2023-08-31 | GL Unit |  | Resources SCO Budgetary/Legal Basis Year-End Procedure Manual and Year-End Checklist
126 | Run a Trial Balance period 998 using Mod & BLL ledgers | 2023-08-31 | GL Unit |  | Compare the ending balances for all accounts. The difference should only be for the encumbrances populated in the BLL Trial Balance, which should post to liabilities and expenditures
127 | Year-end meetings | 2023-08-31 | A.O.
SUBMIT YEAR-END FINANCIAL REPORTS:
128 | Year-End Financial Reports for All Funds due to SCO | 2023-08-31 | GL Unit |  | Deadline to submit Year-End Financial Reports to SCO. Refer to Budget Letter 23-02
129 | Report 13 - Departments must submit to Department of Finance's Fiscal Systems & Consulting Unit (FSCU) & no longer required to submit to SCO | 2023-08-31 | GL Unit |  | Refer to Budget Letter 23-02 (The Report13 may be submitted electronically to FSCU Hotline@dof.ca.gov)
130 | Report 14 - Departments must electronically submit report to the State Treasurer's Office through FI$Cal. | 2023-08-31 | GL Unit |  | Refer to Budget Letter 23-02
131 | Request FSC to Budget Close Reverting Appropriations | 2023-09-06 | Department/FSC |  | Include in the request specific reverted appns and revenue Continuous Appn - provide amount to be rolled over to the new budget year based on YE reports. Fixed Expenditures - Request to zero budget.
132 | Run Allocations for Period 1 | 2023-09-07 | Department
133 | Run AM Depreciation for Period 1 | 2023-09-07 | Department
134 | Request to Close GL/AM for period 1 | 2023-09-08 | Department/FSC
135 | Perform all reconciliations for July (period 1) | 2021-09-08 | A.O.
136 | Fund Balance Reconciliation (DF-303) | 2023-10-01 | Budget Unit |  | Deadline to submit DF-303 to Department of Finance: Refer to link below
FI$Cal Resources for Accounting ¦ Department of Finance
137 | Generally Accepted Accounting Principal (GAAP) information, excluding independently audited financial statements, due to SCO | 2023-10-15 | GL Unit |  | Deadline to submit GAAP information to SCO. Refer to Budget Letter 23-02
138 | GAAP - Independently audited financial statements. If the financial statements are not available by this date, a draft statement must be submitted. | 2023-11-01 | GL Unit |  | Deadline to submit independently audited financial statements to SCO. Refer to Budget Letter 23-02
139 | GAAP - Final independently audited financial statements. | 2023-11-15 | GL Unit |  | Deadline to submit final independently audited financial statements to SCO. Refer to Budget Letter 23-02
REMINDERS:
141 | Verify all real FI$Cal accounts, (UCM GLs 1xxx thru 5xxx series) on the Trial Balance agree with Report 8 submitted with the Financial Statements. | After Financial Reports are submitted to SCO | GL Unit |  | *FI$Cal Trial Balance Accounts Payable+Accrued Payables+Enc=Report 8 GL3010 Accounts Payable *FI$Cal Trial Balance Fund Balance+Enc=Report 8 GL55XX Fund Balance
142 | Manual Reversal of Adjusting Entries (MODACCRL) unless Auto Reverse was used. | After Financial Reports are submitted to SCO | GL Unit |  | Validate - reversals were posted in period 01
143 | Manual Reversal of Year-End Recording of PFA (MODACCRL) unless Auto Reverse was used | After Financial Reports are submitted to SCO | GL Unit |  | Validate - reversals were posted in period 01
144 | Run a current year Trial Balance for period 1 | After Financial Reports are submitted to SCO | GL Unit |  | Compare the beginning balance with last year ending balance. GLs 11xxxxx - 39xxxxx
145 | Evaluate Work Plan | After Financial Reports are submitted to SCO | A.O. |  | Review what worked and how to improve for the next year-end process
NOTE | Agency can close current year submodules even if agency has not completed Year End.
Agency can run current year labor even if agency has not completed Year End.